## Slide 1
MON |  |  |  | 
TUE |  |  |  | 
WED |  |  |  | 
THU |  |  |  | 
FRI |  |  |  | 
WHY CLIENT CLOSE PARTICIPATION IS ESSENTIAL:
Short Timeframe: for this short-term project, commitment is crucial to meet tight deadlines and deliver results quickly
Timely Decision-Making: With limited time, quick and informed decisions are essential to avoid delays
High-Stakes Decisions: decisions made during this project will have a significant impact business; active participation ensures they are well-informed and aligned with goals
Maximizing Value: combine Accenture and CLIENT insights and expertise maximize value derived
INFORMATION: understand context and current scenario and obtain critical information and data to execute analysis
INSIGHTS: refine key findings and strategies
VALIDATION: assumptions and directions to ensure strategic alignment
WS
WORKSHOPS
16-19 Sep
09-13 Sep
02-06 Sep
26-30 Aug
Sep 19th Presentation with Europe Team
Kick-off Meeting
Meetings with Stakeholders: Drivers
Interviews: Drivers & Ambitions
Current Context - CLIENT
Current Context - CLIENT
Team Discussion: hypothesis & scenarios
Executive Checkpoint:
Growth hypothesis, Scenarios Definition and KPIs Confirmation
Team Alignment: workshop review
Executive Checkpoint: Consolidated Strategy Final Deck
Executive Checkpoint: Consolidated Strategy Final Deck (1st version)
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
Daily: team alignment
WS
WS
WS
Executive Checkpoint:
Scenarios overview and final deck planning
WS
Foundation Guidelines
WS
Scenario #1 Deep Dive
WS
Scenario #3 Deep Dive
WS
Scenario #2 Deep Dive
WS
Team Alignment: workshop review
Team Discussion: Financial Modeling
Team Discussion: Financial Modeling
Team Discussion: Required Initiatives for Scenarios
Team Alignment: workshop review
Executive Checkpoint:
Scenarios Analysis & Consolidated Strategy Guidelines
WS
Team Discussion: Financial Modeling for Scenarios & Roadmap
Slot for Final Deck adjustments
Senior Tech Specialists
Senior Business Strategist
CFO
CEO
LOGO