## Slide 1
Project Phases | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Current Situation Analysis |  |  |  |  |  |  | 
Scenarios definition & trade-offs |  |  |  |  |  |  | 
Valuation & Execution Plan |  |  |  |  |  |  | 
Milestones |  |  |  |  |  |  | 
Readout: Valuation & roadmap
Strategic ambitions for CAE business
Internal capabilities assessment
Dependency mapping
Setup
Data Request Submission
Interviews scheduling
Preliminary working sessions with Itaú Chile
Known pain points & limitations of NCG solution
Detailed mapping of current cost baseline
Total cost to implement
Technical feasibility & risks
Timeline to full operation
Required internal capabilities
Benefits vs. current state
Consolidation
Valuation methodologies
Negotiation strategy & levers
Acceptable price range definition
Risk mitigation actions
Execution roadmap & next steps
For each scenario:
Readout: Critical requirements & constraints
Readout: Scenarios comparison analysis
Checkpoint: Analysis progress
Kick-off